Agenda

|  |  |  |
| --- | --- | --- |
| S/No   | Activity  | Timeframe  |
| 1  | Activation of workshops’ funds   | November 13 – 18/2023  |
| 2  | Trainees’ recruitment and grouping   | November 19 – 25/2023  |
| 3  | Literature review, group discussion, research topic selection, and framing research questions    | 26th November to 15th December, 2023  |
| 4  | Communication with Olympic Hotel, and arrangement of training hall    | December 16 and 17, 2023  |
| 5  | **Phase I Training** [*Fundamentals of Qualitative Research Methods in Healthcare focusing Nursing and Midwifery]*  | December 18 – 22/2023  |
| 6  | Developing four qualitative research proposals; securing ethical review and approval   | 23rd December 2023 to 9th February 2024  |
| 7  | **Phase II Training** [Interview guide preparation, validation & piloting]    | February 12 – 16/2024  |
| 8  | Qualitative data collection, transcription and translation  | 17th February to 17th March 2024  |
| 9  | **Phase III Training** [Qualitative data analysis and manuscript writing]    | March 18 – 22/2024  |
| 10  | Manuscript review and finalization   | 23rd March to 15th April 2024  |
| 11  | Writing project final report and financial statement (liquidation)      | April 16 – 22/2024  |
| 12  | Policy brief preparation  | April 23 – 26/2024  |
| 13  | Conducting policy dialogue    | April 29, 2024  |
| 14  | Official closure of the GRN-Pump Priming Workshops     | April 30, 2024  |
| 15  | Submission of four qualitative research manuscripts and one policy brief for publications in peer-reviewed journals   | May 1 onwards   |