Agenda

|  |  |  |
| --- | --- | --- |
| S/No | Activity | Timeframe |
| 1 | Activation of workshops’ funds | November 13 – 18/2023 |
| 2 | Trainees’ recruitment and grouping | November 19 – 25/2023 |
| 3 | Literature review, group discussion, research topic selection, and framing research questions | 26th November to 15th December, 2023 |
| 4 | Communication with Olympic Hotel, and arrangement of training hall | December 16 and 17, 2023 |
| 5 | **Phase I Training** [*Fundamentals of Qualitative Research Methods in Healthcare focusing Nursing and Midwifery]* | December 18 – 22/2023 |
| 6 | Developing four qualitative research proposals; securing ethical review and approval | 23rd December 2023 to 9th February 2024 |
| 7 | **Phase II Training** [Interview guide preparation, validation & piloting] | February 12 – 16/2024 |
| 8 | Qualitative data collection, transcription and translation | 17th February to 17th March 2024 |
| 9 | **Phase III Training** [Qualitative data analysis and manuscript writing] | March 18 – 22/2024 |
| 10 | Manuscript review and finalization | 23rd March to 15th April 2024 |
| 11 | Writing project final report and financial statement (liquidation) | April 16 – 22/2024 |
| 12 | Policy brief preparation | April 23 – 26/2024 |
| 13 | Conducting policy dialogue | April 29, 2024 |
| 14 | Official closure of the GRN-Pump Priming Workshops | April 30, 2024 |
| 15 | Submission of four qualitative research manuscripts and one policy brief for publications in peer-reviewed journals | May 1 onwards |