## Version Control
Document Title | CEPI MSC Rapid Response Framework
Version History
Version number | Effective Date | Description of Change
1 | 2024-07-11 | New Document
2 | September 9, 2025 | Updated to be aligned with published article

## Intro
Intro to MSC Rapid Response Framework
CEPI's CMC rapid response framework is designed for accelerated scenarios including 100 days, where multiple CMC and related activities are conducted almost simultaneously.
It requires a thorough understanding of the necessary tasks when an outbreak occurs and/or a public health emergency is declared. Three rapid response scenarios are prepared
to simulate roadmaps for conditional approval and market authorization of vaccines (Figure below). CMC-related activities are highlighted in orange in the figure. The framework
provides tailored CMC checklists for pandemic preparedness and key deliverables for accelerated vaccine development, manufacturing, and roll-out for the scenarios, focusing on
the activities in the yellow-frame.
The rapid response frameworks are divided into five technical development areas: (1) drug substance (DS) and drug product (DP) process, (2) formulation and stability, (3) analytical methods,
(4) material controls and supply chain, and (5) manufacturing and facilities. We propose using this framework as guidance to streamline CMC and related activities during pandemic preparation
and outbreak response phases. Additionally, we anticipate that the framework could serve vaccine developers as a tool to identify areas for improvement and innovation for rapid
response and as a benchmark to assess preparedness levels.
The additional discussion on the rapid response framework can be found in an article published in Vaccines ( DOI: 10.3390/vaccines13080849 ).

## DSDP Process
Drug Substance & Drug Product Process
| # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments
| 1.1 | Preparation during the interpandemic period |  |  | 1.2 | The 100-day scenario |  |  | 1.3 | The 100-day scenario |  |  | 1.4 | The 100-day scenario |  |  | 2.1 | The 150 - 180 day scenario |  |  | 2.2 | The 150 - 180 day scenario |  |  | 2.3 | The 150 - 180 day scenario |  |  | 3.1 | The 200-230 day scenario |  |  | 3.2 | The 200-230 day scenario |  |  | 3.3 | The 200-230 day scenario
High level definition |  | Platform development / Innovation during interpandemic period, based on CMC Framework |  |  |  | CTM manufacturing for phase 2b/3 |  |  |  | Process validation (PV) for conditional approval |  |  |  | Post-conditional approval commitment for marketing authorization (the second 100 days) |  |  |  | GLP manufacturing for preclinical evidence generation and toxicology |  |  |  | Manufacturing for phase 1/2a |  |  |  | Phase 2b/3, PV for conditional approval, and post-conditional approval - Same as the 100-day scenario |  |  |  | Antigen design |  |  |  | Preclincal Evidence Generation and Phase 1/2a trial - Same as the 150 - 180 day scenario |  |  |  | Phase 2b/3, PV for conditional approval, and post-conditional approval - Same as the 100-day scenario
Expected requirements (M) | A | Platform manufacturing processes established and consulted with HAs |  |  | A | Manufacturing DS/DP using platform process at scale, yielding sufficient doses for Phase 2b/3. |  |  | A | Conducting PV per HA consultation |  |  | A | Continue PV to meet HA commitment |  |  | A | GLP manufacturing using platform manufacturing process |  |  | A | Manufacturing DS/DP using platform process, yielding sufficient doses for Phase 1/2a | [6 empty] | A | Choose a suitable platform for vaccine candidate
| B | → Platform manufacturing process characterization with vaccine candidates |  |  | B | → Manufacture WCB / WVS, in consideration of manufacturing billions of doses in case of pandemic response. |  |  | B | Manufacturing consistency of the vaccine candidate demonstrated |  |  | B | Continue consultation with HA for post-marketing authorization commitment |  |  | B | Platform fit with antigen demonstrated |  |  | B | → Establish/test MCB and WCB in parallel at risk, if necessary | [6 empty] | B | Rapid gene synthesis and antigen expression executed
| C | → CQAs, CPPs, PAR and NOR defined based on platform experience |  |  | C | DS/DP released using platform analytical release and specification |  |  | C | Continue consultation with HA for conditional approval strategy and post-conditional approval commitments |  |  | C | Process optimization and list of changes submitted per the post-approval commitment |  |  | C | Initiate tech transfer to GMP facility for CTM manufacturing |  |  | C | → Establish/test MVS and WVS in parallel at risk, if necessary | [6 empty] | C | High-throughput in vitro screening tools in place
| D | → Data consistency from PV using platform processes |  |  | D | Continue consultation with HAs for IND approval / PV strategy |  |  | D | Application for conditional approval submitted |  |  | D | Continue risk assessment for vaccine |  |  | D | Initiate consultation with HAs for IND and preclinical / clinical strategies (pre-IND consultation) |  |  | D | DS/DP released using platform analytical release and specification | [6 empty] | D | Lab-scale production for manufacturability, platform fit assessment, and PoC animal study
| E | → Market authorization obtained with a minimal number of vaccine candidates if feasible |  |  | E | Comparability demonstrated with previous batches |  |  | E | Continue risk assessment for vaccine candidate | [6 empty] | E | Develop a life-cycle management plan for vaccine candidate |  |  | E | Comparability protocol in place | [6 empty] | E | Risk assessment of vaccine development initiated
| F | → Platform QTPP identified |  |  | F | Comparability protocol in place, (for phase 2b/3, PV, commercial and tech transferred batches) | [10 empty] | F | Risk assessment developed for vaccine candidate |  |  | F | Continue consultation with HAs for IND approval / clinical trial strategy
| G | → Viral clearance validated for platform, if appropriate |  |  | G | Platform process fit with the vaccine candidate demonstrated | [14 empty] | G | IND/IMPD for phase 1/2a submitted
| H | Establish platform tech transfer |  |  | H | → Platform viral clearance verified, if appropriate | [14 empty] | H | Continue risk assessment for vaccine candidate
| I | → Platform manufacturing process description, MBR and other documentation required for GMP manufacturing, appropriate for any clinical phase and commercialization |  |  | I | IND/IMPD for phase 2b/3 submitted
| J | → Tech transfer strategy and protocol developed for platform and executed, if appropriate. |  |  | J | Tech transfer to regional manufacturers, if appropriate
| K | Develop stable cell lines and/or master cell banks of priority and/or prototype vaccines / disease X library, if appropriate |  |  | K | → Train workforce for tech transfer SME
| L | Develop viral stocks of priority and prototype pathogens, if applicable |  |  | L | Risk register developed, specific for vaccine candidate
| M | Comparability strategy discussed with HAs and established
| N | → Platform database prepared with comparability between engineering, phase 1/2a CTM and other CTM batches for vaccine candidates
| O | IND/IMPD and BLA templates developed
| P | Develop risk-based product lifecycle plans
| Q | → Manage platform risk assessment
| R | → Continue platform optimization
| S | Train workforce to develop SME
| T | Rolling QA review process established
Additional Considerations (N) | A | Process innovation for 100 Days Mission - speed, for example |  |  | A | CoGs confirmed with the vaccine candidate |  |  | A | Tech transfer to regional manufacturers, if appropriate | [6 empty] | A | If platform fit is not achieved, optimize and update process and control strategies for vaccine candidate |  |  | A | Tech transfer to regional manufacturers, if necessary
| B | Develop prototype vaccines/ disease X library using platform process |  |  | B | If platform fit is not demonstrated at scale, optimize and update process and control strategies for vaccine candidate | [10 empty] | B | Initiate cell line development, if necessary |  |  | B
| C | Develop manufacturing strategies with alternative technologies to SCL/MCB | [14 empty] | C | Master cell bank manufactured/ released, if necessary
| D | → Comparability assessed between alternative technologies (such as transient) and conventional processes using SCL/MCB.
| E | Investigational reserve/ stockpile of vaccine candidates prepared, if appropriate
The symbol → and increased indentation describes additional deliverables for the activity listed above.

## Formulation and stability
Formulation & Stability
| # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments
| 1.1 | Preparation during the interpandemic period |  |  | 1.2 | The 100-day scenario |  |  | 1.3 | The 100-day scenario |  |  | 1.4 | The 100-day scenario |  |  | 2.1 | The 150 - 180 day scenario |  |  | 2.2 | The 150 - 180 day scenario |  |  | 2.3 | The 150 - 180 day scenario |  |  | 3.1 | The 200-230 day scenario |  |  | 3.2 | The 200-230 day scenario |  |  | 3.3 | The 200-230 day scenario
High level definition |  | Platform development / Innovation during interpandemic period, based on CMC Framework |  |  |  | CTM manufacturing for phase 2b/3 |  |  |  | Process validation (PV) for conditional approval |  |  |  | Post-conditional approval commitment for marketing authorization (the second 100 days) |  |  |  | GLP manufacturing for preclinical evidence generation and toxicology |  |  |  | Manufacturing for phase 1/2a |  |  |  | Phase 2b/3, PV for conditional approval, and post-conditional approval - Same as the 100-day scenario |  |  |  | Antigen design |  |  |  | Preclincal Evidence Generation and Phase 1/2a trial - Same as the 150 - 180 day scenario |  |  |  | Phase 2b/3, PV for conditional approval, and post-conditional approval - Same as the 100-day scenario
Expected requirements (M) | A | Platform formulation (including, e.g., adjuvants) established, consulted with HAs |  |  | A | Initiate DS/DP stability of phase 2b/3 CTM |  |  | A | Continue CTM stability testing and demonstrate alignment with platform stability experience |  |  | A | Stability continued and aligned with platform stability experience |  |  | A | Compatibility of platform formulation and adjuvant demonstrated with atigen, if necessary |  |  | A | Initiate DS/DP stability of phase 1a/2 CTM | [6 empty] | A | Platform formulation identified
| B | Platform DP presentation defined |  |  | B | Conduct accelerated stability of phase 2b/3 CTM |  |  | B | Conduct real-time stability of validation batches |  |  | B | Revisit shelf-life with vaccine candidate for possible extension |  |  | B | GLP material real-time stability and accelerated stability initiated |  |  | B | Conduct accelerated stability of phase 1/2a CTM | [6 empty] | B | Formulation compatibility with vaccine candidates evaluated
| C | → Adjuvants compatibility with various vaccine candidates demonstrated |  |  | C | Shelf-life established with the vaccine candidate, based on phase 1 batch or platform formulation, if appropriate |  |  | C | Conduct accelerated stability of selected validation batches |  |  | C | Continue risk assessment for vaccine candidate- specific formulation |  |  | C | Risk registers developed for vaccine candidate- specific formulation |  |  | C | Shelf-life established with the vaccine candidate | [6 empty] | C | Platform stability fit assessed
| D | → DS/DP Stability for platform demonstrated |  |  | D | Risk registers developed for vaccine candidate- specific formulation |  |  | D | Extend shelf-life with the vaccine candidate per stability results | [10 empty] | D | Continue risk assessment for vaccine candidate- specific formulation | [6 empty] | D | → Vaccine candidate stability study initiated (real-time and accelerated conditions) in parallel
| E | → In-use stability for platform demonstrated | [6 empty] | E | Continue risk assessment for vaccine candidate-specific formulation | [19 empty] | Risk registers developed for vaccine candidate specific formulation
| F | → Accelerated stability for platform conducted
| G | → Primary packaging validated (CCIT, dose recovery, leachable/extractables) with various vaccine candidates
| H | Shelf-life determined with platform formulation
| I | Risk registers developed for platform and/or vaccine candidate-specific formulation
| J | Train workforce to develop SME
| K | Rolling QA review process established
Additional Considerations (N) | A | Formulation innovation - thermal stability, for example |  |  | A | In-use stability demonstrated with the vaccine candidate, if appropriate
| B | Evaluate adjuvants from adjuvant library |  |  | B | Validate the stability model with vaccine candidate-specific stability data
| C | Develop and validate stability model, if appropriate
The symbol → and increased indentation describes additional deliverables for the activity listed above.

## Analytical
Analytical
| # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments
| 1.1 | Preparation during the interpandemic period |  |  | 1.2 | The 100-day scenario |  |  | 1.3 | The 100-day scenario |  |  | 1.4 | The 100-day scenario |  |  | 2.1 | The 150 - 180 day scenario |  |  | 2.2 | The 150 - 180 day scenario |  |  | 2.3 | The 150 - 180 day scenario |  |  | 3.1 | The 200-230 day scenario |  |  | 3.2 | The 200-230 day scenario |  |  | 3.3 | The 200-230 day scenario
High level definition |  | Platform development / Innovation during interpandemic period, based on CMC Framework |  |  |  | CTM manufacturing for phase 2b/3 |  |  |  | Process validation (PV) for conditional approval |  |  |  | Post-conditional approval commitment for marketing authorization (the second 100 days) |  |  |  | GLP manufacturing for preclinical evidence generation and toxicology |  |  |  | Manufacturing for phase 1/2a |  |  |  | Phase 2b/3, PV for conditional approval, and post-conditional approval - Same as the 100-day scenario |  |  |  | Antigen design |  |  |  | Preclincal Evidence Generation and Phase 1/2a trial - Same as the 150 - 180 day scenario |  |  |  | Phase 2b/3, PV for conditional approval, and post-conditional approval - Same as the 100-day scenario
Expected requirements (M) | A | Platform analytical methods (In-process, release, stability and characterization) established for DS/DP |  |  | A | QTPP finalized for the vaccine candidate |  |  | A | Complete analytical validation per HA consultation |  |  | A | Complete commitment of post - conditional approval |  |  | A | QTPP for vaccine candidate proposed, in consideration of TPP |  |  | A | Continue to develop and qualify vaccine-specific methods, if necessary | [6 empty] | A | Platform analytical methods identified
| B | Platform (master) release specifications established for DS/DP |  |  | B | Platform analytical fit with the vaccine candidate demonstrated |  |  | B | Continue consultation with HA for conditional and marketing authorization |  |  | B | Consult HA for post-marketing authorization commitment (such as updating specification/criteria, testing methods, etc) |  |  | B | Analytical platform fit with vaccine candidate demonstrated |  |  | B | Reference standard strategy in place | [6 empty] | B | Platform analytical method fit assessed
| C | → Platform assays and data discussed with HAs |  |  | C | Specification justified for the vaccine candidate |  |  | C | Continue risk assessment for vaccine candidate-specific analytical methods |  |  | C | Tech transfer to NCLs |  |  | C | Platform IPC and IPM justified with vaccine candidate |  |  | C | Tox material shown to be representative of Phase 1/2a CTM | [6 empty] | C | Initiate vaccine candidate-specific assay development
| D | Phase-appropriate validation for platform assays performed. |  |  | D | Reference standard strategy in place | [6 empty] | D | Continue risk assessment for vaccine candidate- specific analytical methods |  |  | D | Platform release specification justified with vaccine candidate |  |  | D | Analytical comparability strategy and protocol in place (for phase1/2a and later GMP batches) | [6 empty] | D | Risk registers developed for vaccine candidate- specific analytical methods
| E | Develop vaccine-specific assays (such as potency and ID assays) for prototype, exemplar vaccines / disease X library, if appropriate |  |  | E | Analytical comparability with previous batches evaluated | [10 empty] | E | Develop and qualify vaccine-specific analytical methods |  |  | E | Update QTPP for vaccine candidate, if necessary
| F | Rapid release methods developed and validated in phase-appropriate manner |  |  | F | Comparability protocol in place (for phase2b/3, PV, commercial and tech transferred batches) | [10 empty] | F | Analytical tech transfer to QC lab(s) |  |  | F | Continue risk assessment for vaccine candidate- specific analytical methods
| G | Analytical tech transfer protocol developed and executed with at least one vaccine candidate |  |  | G | Develop and qualify vaccine-specific analytical methods, if necessary | [10 empty] | G | Analytical lifecycle management strategy for vaccine candidate in place
| H | Comparability strategy discussed/ established |  |  | H | Analytical validation of critical tests | [10 empty] | H | Preliminary reference standard in place for CTM release
| I | HA consultation for rapid response analytical strategy |  |  | I | Continue consultation with HA analytical validation strategy for conditional approval | [10 empty] | I | Risk registers developed for vaccine candidate- specific analytical methods
| J | Analytical lifecycle management strategy in place |  |  | J | Analytical tech transfer to regional manufacturers, if necessary
| K | Risk registers developed for platform and/or vaccine candidate-specific analytical methods |  |  | K | Risk registers developed for vaccine candidate- specific analytical
| L | Train workforce to develop SME
| M | Rolling QA review process established
Additional Considerations (N) | A | Analytical innovation - high-throughput, automation, etc | [6 empty] | A | Tech transfer to NCLs | [6 empty] | A | Optimize analytical methods, if platform fit not justified
| B | Identify and qualify analytical CROs for vaccine-specific method development and characterization | [14 empty] | B | Optimize IPC or IPM, if platform fit is not justified
The symbol → and increased indentation describes additional deliverables for the activity listed above.

## Material Controls&Supply Chain
Materials & Supply chain
| # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments
| 1.1 | Preparation during the interpandemic period |  |  | 1.2 | The 100-day scenario |  |  | 1.3 | The 100-day scenario |  |  | 1.4 | The 100-day scenario |  |  | 2.1 | The 150 - 180 day scenario |  |  | 2.1 | The 150 - 180 day scenario |  |  | 2.2 | The 150 - 180 day scenario |  |  | 2.3 | The 150 - 180 day scenario |  |  | 3.1 | The 200-230 day scenario |  |  | 3.2 | The 200-230 day scenario |  |  | 3.3 | The 200-230 day scenario
High level definition |  | Platform development / Innovation during interpandemic period, based on CMC Framework |  |  |  | CTM manufacturing for phase 2b/3 |  |  |  | Process validation (PV) for conditional approval |  |  |  | Post-conditional approval commitment for marketing authorization (the second 100 days) |  |  |  | GLP manufacturing for preclinical evidence generation and toxicology |  |  |  | GLP manufacturing for preclinical evidence generation and toxicology |  |  |  | Manufacturing for phase 1/2a |  |  |  | Phase 2b/3, PV for conditional approval, and post-conditional approval - Same as the 100-day scenario |  |  |  | Antigen design |  |  |  | Preclincal Evidence Generation and Phase 1/2a trial - Same as the 150 - 180 day scenario |  |  |  | Phase 2b/3, PV for conditional approval, and post-conditional approval - Same as the 100-day scenario
Expected requirements (M) | A | Platform raw materials and consumables defined (Bill of Materials) |  |  | A | Raw material supplies secured for manufacturing |  |  | A | Raw material supplies secured for process validation |  |  | A | Supply chain strategy for post-marketing authorization commitment defined |  |  | A |  |  |  | A | Raw materials used for GLP manufacturing representative of GMP raw materials |  |  | A | Raw material supplies secured for manufacturing | [7 empty] | Raw materials and consumables required for manufacturing identified |  |  | A
| B | → Raw material & consumables' suitability / origins defined |  |  | B | → Critical or special/single-source raw materials identified and supply secured. |  |  | B | → Raw material stocks established suitable for process validation per risk registers |  |  | B | Shipping validation (product-specific) |  |  | B |  |  |  | B | Risk registers developed for product-specific raw materials |  |  | B | → Critical or special/single-source raw materials identified and supply secured. | [7 empty] | Suppliers identified |  |  | B
| C | → Multicompendial-grade (high-quality) raw material availability ensured |  |  | C | Cold chain storage and shipping strategy to clinical sites established |  |  | C | Cold chain storage and shipping strategy for global supply established |  |  | C | Secondary packaging updated and ready for commercialization |  |  | C | [7 empty] | C | Cold chain storage and shipping strategy to clinical sites established | [7 empty] | Supply chain risk assessment initiated |  |  | C
| D | → Risk assessment performed for critical raw materials |  |  | D | Risk registers developed for product-specific raw or starting materials |  |  | D | Secondary packaging developed | [6 empty] | D | [16 empty] | Purchase orders issued |  |  | D
| E | → Critical material attibutes defined | [14 empty] | E
| F | Platform starting materials defined
| G | → Release specifications established | [14 empty] | F
| H | → Origin of starting materials defined | [14 empty] | H
| I | Adjuvants identified and suppliers established, if applicable
| J | Analytical reagents defined and suppliers identified | [14 empty] | I
| K | License agreement in place, if required | [14 empty] | J
| L | Supply chain defined and qualified per CMC Framework - Supply chain & COGS | [14 empty] | K
| M | Risk registers of raw materials for platform- and product-specific development | [14 empty] | L
| N | Alternative raw material suppliers idenfied and qualified, based on risk registers | [14 empty] | M
| O | → Identify and qualify multiple suppliers of critical raw materials | [14 empty] | N
| P | → Maintain inventory necessary for rapid response | [14 empty] | O
| Q | Train workforce to develop SME | [14 empty] | P
| R | Rolling QA review process established | [14 empty] | Q
Additional Considerations (N) | A | Primary packaging defined and validated |  |  | A | Raw material batch-to-batch comparability evaluated |  |  | A | Raw material batch-to-batch comparability evaluated |  |  | A | Alternative raw material suppliers idenfied and qualified, if appropriate |  |  | A | [7 empty] | A | Alternative raw material suppliers idenfied and qualified, if necessary
| B | Shipping validation strategy in place and conducted, if appropriate | [6 empty] | B | Alternative raw material suppliers idenfied and qualified, if appropriate | [6 empty] | B
The symbol → and increased indentation describes additional deliverables for the activity listed above.

## Manufacturing&Facilities
Facilities & Manufacturing
| # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments | # | Deliverables for | Status | Comments
| 1.1 | Preparation during the interpandemic period |  |  | 1.2 | The 100-day scenario |  |  | 1.3 | The 100-day scenario |  |  | 1.4 | The 100-day scenario |  |  | 2.1 | The 150 - 180 day scenario |  |  | 2.2 | The 150 - 180 day scenario |  |  | 2.3 | The 150 - 180 day scenario |  |  | 3.1 | The 200-230 day scenario |  |  | 3.2 | The 200-230 day scenario |  |  | 3.3 | The 200-230 day scenario
High level definition |  | Platform development / Innovation during interpandemic period, based on CMC Framework |  |  |  | CTM manufacturing for phase 2b/3 |  |  |  | Process validation (PV) for conditional approval |  |  |  | Post-conditional approval commitment for marketing authorization (the second 100 days) |  |  |  | GLP manufacturing for preclinical evidence generation and toxicology |  |  |  | Manufacturing for phase 1/2a |  |  |  | Phase 2b/3, PV for conditional approval, and post-conditional approval - Same as the 100-day scenario |  |  |  | Antigen design |  |  |  | Preclincal Evidence Generation and Phase 1/2a trial - Same as the 150 - 180 day scenario |  |  |  | Phase 2b/3, PV for conditional approval, and post-conditional approval - Same as the 100-day scenario
Expected requirements (M) | A | GMP clinical and commercial manufacturing site(s) for DS/DP in the region(s) identified and qualified |  |  | A | CTM manufacturing site(s) identified and slots secured |  |  | A | Site(s) in compliance with applicable HA regulations |  |  | A | Site(s) in compliance with applicable HA regulations |  |  | A |  |  |  | A | Vaccine developer(s) and pilot facility (ies) identified |  |  | A | CTM manufacturing site(s) identified |  |  | A | Phase 1/2a CTM manufacturing sites identified
| B | → Contract in place for access in emergency |  |  | B | Site(s) in compliance with applicable HA regulations | [6 empty] | B | Pre-approval inspection (PAI) completed |  |  | B | [7 empty] | B | Site(s) in compliance with applicable HA regulations |  |  | B | Phase 2b/3 CTM and commercial manufacturing sites in screening
| C | QC labs in region(s) identified and qualified |  |  | C | → Site(s) inspected and GMP-certified by local authoritie(s) for vaccine candidate manufacturing | [6 empty] | C | Fullfill HA commitments for conditional approval |  |  | C | [7 empty] | C | → Site(s) inspected and GMP certified by local authoritie(s) for vaccine candidate manufacturing |  |  | C | Manufacturing and tech transfer risk assessment initiated
| D | → Contract in place for access in emergency |  |  | D | QC lab(s) identified and resources secured | [6 empty] | D | Consult with HA for post-marketing authorization commitment for manufacturing sites and QC laboratories |  |  | D | [7 empty] | D | QC lab(s) identified |  |  | D | QC lab(s) identified or in screening
| E | Site(s) in compliance with applicable HA regulations | [14 empty] | E
| F | Platform manufacturing process and analytical methods transferred
| G | → Facility fit assessed | [14 empty] | F
| H | → Risk assessment initiated | [14 empty] | H
| I | Live fire drill to confirm successful execution of various process steps, if applicable | [14 empty] | I
| J | Train workforce and develop SME | [14 empty] | J
| K | Rolling QA review process established | [14 empty] | K
Additional Considerations (N) | A | Perform process validation using the platform to gain PV experience | [6 empty] | A | Identify and secure slots at regional manufacturers, if appropriate | [6 empty] | A
| B | Optimize processes per live fire drill experience, if appropriate | [14 empty] | B

## CEPI-Intro (hidden)
CEPI 2.0 CMC framework V03
Revision history
| ISSUE | Date | Description of changes
V01 | 1 | 28/06/2022 | Initial draft CEPI 2.0 CMC framework
V01 | 2 | 2022-08-12 | Issue for wider team review. Pending adjustment to new iPDP WP structure
V01 | 3 | 2022-10-21 | Finalization CEPI 2.0 CMC framework V01
V02 | V02:1 | 2023-02-15 | Draft including new feedback from SC team
V02 | V02:2 | 2023-02-28 | Finalization CEPI 2.0 CMC framework V02
V03 | V03:1 | 2023-09-05 | Adaptation disregarding CEPI WP structure and thorough review of deliverables. Draft for wider review.
V03 | V03:2 | 2023-09-25 | Draft including updated intro sheets and a sheet for reviewer comments
V03 | V03 | 2023-09-29 | Finalization CEPI 2.0 CMC framework V03
DRAFT
The CMC framework is intended to be a guideline to track progression of CMC activities within CEPI vaccine development projects.
CMC activities for CEPI CMC Innovations and MSCN projects will need to be adapted accordingly.
The next tabs show the recommended deliverables ('Expected requirements' and 'Additional Considerations') for each category (i.e. manufacturing process, formulation & stability, analytics, supply chain & COGs, facility & compliance) that are considered beneficial to fulfill during the different development phases. This update (V03 29Sep2023) includes numerous updates based on comments provided (https://cepino.sharepoint.com/:x:/r/sites/EXTCMCTeam/Shared%20Documents/2.%20Templates%20Databases%20and%20Internal%20Guidance/CMC%20Framework/2023_V03/Archived_Working%20versions%20V03/CMC%20Framework%20recommended%20changes%20from%20V02%20to%20V03.xlsx?d=wa3e3378d0c78474da25b5ae4140d7a87&csf=1&web=1&e=grVfZL), and the major shift is that it is no longer aligned with CEPI stage gates but aiming to list CMC activities to be done in preparation for each clinical phase. This file will be adopted for publication, removing CEPI specific deliverables and this CEPI-Intro sheet. It is recognized that there is some variability between CEPI project contracts, so the deliverables to be achieved at different phases should be adpated based on the project specific development plan, e.g. possibilities for data leverage based on platform technologies. It should be noted that several deliveries listed in the CMC framework overlap with regulatory activities.
Unique numbering system
For ease of communicating and tracking CMC deliverables, the following identifier system is to be used:
| Aspect | Phase | Expected requirements/ Additional Considerations | Ref. Letter
e.g. | DS | 1 | M | C | --> | DS1MC
| DS - Drug Substance and Drug Product Process | 0 - Pre-clinical | M - Expected requirements | A to Z - unique identifier
| DP - Adjuvant, F&F, Stability | 1 - Ph I | N - Additional Considerations
| QC - Analytical Maturity | 2 - Ph II
| SC - Supply Chain Maturity & CoGs | 3 - Ph IIb/III
| GMP - Production Facilities | 4 - Ph IV /Post Licensure
5 - Investigational Stockpile
Note that a certain identifier may differ between versions of the framework
Status at Project Review
| Activity on track |  | G
| Activity not on track, to be done at a later phase |  | A
| Activity not complete, risk that it will become a bottleneck |  | R
| Not applicable, or not assessed |  | na
| Activity completed |  | C
Instructions to CMC Leads
Please use this template to create a file for each project, named in the format "CMC Framework V03_CfPx_Awardee_date". This file (once filled out) is to be shared with the PM and kept in Salesforce.
For new projects the framework is introduced during DD, to ensure the proposal and iPDP fulfill the expected requirements.
This generic template may be adapted to suit each project, though it is recommended NOT to delete any "must" deliverables.
Upon creation of the iPDP, make sure that all relevant SG criteria/deliverables are captured appropriately. This might be a good time to introduce the developer to the CMC Framework and CEPI expectations.
In preparation for portfolio review, SG review, etc., please colour code status of deliverables according to the RAG definition above. This may be updated more frequently as the CMC Lead see fit, to give a snapshot of the project CMC status. Rationales for red/amber activities should be given in the comment cell.
A copy or link to the current version of relevant 'linked' files will be placed in the CMC Framework teams folder.

## DS and DP Process (hidden)
Drug Substance & Drug Product Manufacturing Process (DS)
| # | CMC deliverables during | Status | Comments | Rapid Response | # | CMC deliverables for | Status | Comments | Rapid Response | # | CMC deliverables for | Status | Comments | Rapid Response | # | CMC deliverables for | Status | Comments | Rapid Response | # | CMC deliverables for and during | Status | Comments | Rapid Response | # | CMC deliverables for and during | Status | Comments | Rapid Response
| 1.1 | Pre-clinical |  |  |  | 1.2 | Phase I |  |  |  | 1.3 | Phase II |  |  |  | 1.4 | Investigational stockpile |  |  |  | 1.5 | Phase IIb/III pivotal study |  |  |  | 1.6 | Phase IV
High level definition |  | Process suitable for generating material for animal studies |  |  |  |  | Process suitable for first in human |  |  |  |  | Process optimized for phase II |  |  |  |  | Process suitable for investigational stockpile |  |  |  |  | Process validation |  |  |  |  | Post Licensure manufacturing
Expected requirements (M) | A | Develop stable cell line/RCB/Research Viral Seed |  |  | 1 - Preparation | A | Process developed with acceptable yield |  |  | 2- Alert to CTM1 | A | RA & CMC strategy updated |  |  | 2- Alert to CTM1 | A | BDS ready for stockpile |  |  | 4- Post D100 | A | Process robustness demonstrated (#CTMs) |  |  | 3 - For inital auth | A | Dossier for MAA submitted |  |  | 4- Post D100
| B | Genetic stability assessed |  |  | 1 - Preparation | B | MCB/MVS available including characterization report |  |  | 2- Alert to CTM1 | B | Process optimized, scalable, and basic consistency demonstrated (if applicable) |  |  | 3 - For inital auth | B | BDS to final filled product manufacturing protocol in place |  |  | 4- Post D100 | B | Cleaning validation – Limits (TOC, pH & conductivity) established for cleaning samples, CIP and SIP cycles defined |  |  | 4- Post D100 | B | Submissions plan for satisfying eventual commitments/agreements taken during the revision phase prior license approval |  |  | 4- Post D100
| C | Material for TOX studies available |  |  | 2- Alert to CTM1 | C | Engineering lot manufactured |  |  | 2- Alert to CTM1 | C | QTTP updated: CQAs & CPPs, including acceptance criteria, defined |  |  | 3 - For inital auth | C | QTTP updated: CQAs & CPPs including acceptance criteria |  |  | 4- Post D100 | C | WCB and/or WSV established for routine manufacturing. Strategy aligned with RA for LCM/additional passage of cells. |  |  | 4- Post D100 | C | Submission of all the Post approval changes (i.e. Bundle submission) |  |  | 4- Post D100
| D | QTPP available |  |  | 2- Alert to CTM1 | D | Protocol for Phase I manufacturing in place, including process flow diagram |  |  | 2- Alert to CTM1 | D | Initial process technology risk assessment |  |  | 1 - Preparation | D | Appropriate DP filled available (per requirements) |  |  | 4- Post D100 | D | Processs Design Complete, including CPPs/ KPPs, IPC parameters |  |  | 3 - For inital auth | D | Annual Product Quality Review program in place |  |  | 4- Post D100
[6 empty] | E | Phase I CTM manufactured |  |  | 2- Alert to CTM1 | E | Updated Formulation Fill-finish process in place (if applicable) |  |  | 2- Alert to CTM1 | E | Updated IND dossier/ IMPD ready for submission |  |  | 4- Post D100 | E | Equipment train and PFD final |  |  | 3 - For inital auth
[6 empty] | F | RA & CMC strategy available |  |  | 1 - Preparation | F | Protocol based manufacturing of the clinical Phase II batches including DP batches with different doses for dose range studies |  |  | 2- Alert to CTM1 | [5 empty] | F | Product specification file approved |  |  | 3 - For inital auth
[6 empty] | G | IND dossier / IMPD ready for submission |  |  | 3 - For inital auth | G | Media fill test and media simulation as required |  |  | 1 - Preparation | [5 empty] | G | Post mitigation process risk assessment completed |  |  | 4- Post D100
[6 empty] | H | Process description available: Process steps, Materials, Equipment |  |  | 2- Alert to CTM1 | H | Process/product comparability protocol Phase II vs Phase I CTM in place, including overview of process changes |  |  | 2- Alert to CTM1 | [5 empty] | H | End of Production studies (MCB / WCB) |  |  | 4- Post D100
[6 empty] | I | Media fill test and media simulation as required |  |  | 3 - For inital auth | I | Updated IND dossier/ IMPD ready for submission |  |  | 3 - For inital auth | [5 empty] | I | Filter validation protocol available |  |  | 2- Alert to CTM1
[6 empty] | J | Product comparability vs TOX lots |  |  | 2- Alert to CTM1 | [10 empty] | J | Single use / multiple use components defined. Qualification protocol in place for reuse cycles e.g. TFF cassettes, filters, resins & membranes |  |  | 1 - Preparation
[6 empty] | K | Briefing Documentation ready for HA consultation (i.e. pre-IND meetings/Scientific Advices) |  |  | 2- Alert to CTM1 | [10 empty] | K | RA and CMC strategy for licensing and post approval changes aligned |  |  | 3 - For inital auth
[6 empty] | L | Scientific advice from health authorities if using technologies that are novel or without precedence in licensed products |  |  | 1 - Preparation | [10 empty] | L | MBR / record sheets in place |  |  | 3 - For inital auth
[21 empty] | M | Genetic stability and End of Production studies report to be included in module 3 |  |  | 4- Post D100
[21 empty] | N | Updated IND dossier/ IMPD ready for submission |  |  | 3 - For inital auth
[21 empty] | O | Phase IIb/III CTM manufactured, lot-to-lot consistency / PV demonstrated, preferably at commercial manufacturing scale |  |  | 3 - For inital auth
[21 empty] | P | Process validation master plan interim report available (interim since stability studies are ongoing) |  |  | 3 - For inital auth
[21 empty] | Q | Post approval change management - LCM in place |  |  | 4- Post D100
[21 empty] | R | In process hold time established |  |  | 4- Post D100
[21 empty] | S | Media fill test and media simulation as required |  |  | 3 - For inital auth
[21 empty] | T | Product handover to manufacturing (from scale up / MSAT team) and QA (from development QA) |  |  | 3 - For inital auth
[21 empty] | U | Tech transfer protocol approved (if applicable) |  |  | 4- Post D100
[21 empty] | V | E&L risk assessment completed. Studies initiated based on the outcome of risk assessment |  |  | 3 - For inital auth
Additional Considerations (N) | A | TT protocol or MBR draft approved |  |  | 2- Alert to CTM1 | A | Initial characterization report |  |  | 3 - For inital auth | A | Overview of process changes (if applicable) |  |  | 2- Alert to CTM1 | A | Overview of process changes (if applicable) |  |  | 4- Post D100 | A | Continuous process verification protocol in place |  |  | 4- Post D100 | A | Master qualification protocols for Masters and Working seed bank (ideal to be present within the first MAA application) |  |  | 4- Post D100
[6 empty] | B | Process scale up approach (if applicable) |  |  | 3 - For inital auth | B | Risk assessment for E&L |  |  | 3 - For inital auth | [5 empty] | B | Internal mock audit/inspection for pre-approval inspection |  |  | 1 - Preparation
[6 empty] | C | TT strategy and protocol (if applicable) |  |  | 4- Post D100 | C | Monitoring of genetic stability |  |  | 4- Post D100 | [5 empty] | C | DS Inactivation kinetics study report available |  |  | 2- Alert to CTM1
[6 empty] | D | Process technology risk assessment |  |  | 1 - Preparation | D | In process hold time established |  |  | 3 - For inital auth | [5 empty] | D | Online data capture system for the process parameters in place and to support statistical process control. In addition, recommendations as part of local site industry 4.0 objectives to be considered |  |  | 4- Post D100
Pre-clinical
Phase I
Phase II
Phase IIb/III pivotal study
Investigational Stockpile
Phase IV /post licensure

## Formulation & Stability (hidden)
Drug Substance & Drug Product Formulation and Stability (DP)
| # | CMC deliverables during | Status | Comments | Rapid Response | # | CMC deliverables for | Status | Comments | Rapid Response | # | CMC deliverables for | Status | Comments | Rapid Response | # | CMC deliverables for | Status | Comments | Rapid Response | # | CMC deliverables for and during | Status | Comments | Rapid Response | # | CMC deliverables for and during | Status | Comments | Rapid Response
| 2.1 | Pre-clinical |  |  |  | 2.2 | Phase I |  |  |  | 2.3 | Phase II |  |  |  | 2.4 | Investigational stockpile |  |  |  | 4.5 | Phase IIb/III pivotal study |  |  |  | 2.6
High level definition |  | Product suitable for intended administration route for animal studies |  |  |  |  | Product suitable for first in human |  |  |  |  | Product suitable for Phase II |  |  |  |  | Product suitable for Emergency Use |  |  |  |  | Final formulation according to TPP |  |  |  |  | Licensed Product
Expected requirements (M) | A | TOX/Phase I formulation developed, suitable for intended administration route (pH, osmolality, excipient quality, etc.) |  |  | 1 - Preparation | A | In-use stability suitable for phase I specified |  |  | 2- Alert to CTM1 | A | Real-time stability studies initiated for phase II CTM DS & DP |  |  | 3 - For inital auth | A | Investigational stockpile storage condition and shelf life defined |  |  | 2- Alert to CTM1 | A | Formulation development completed |  |  | 3 - For inital auth | A | Annual product stability program in place |  |  | 4- Post D100
| B | FT stable formulation (if applicable) |  |  | 1 - Preparation | B | Real-time stability studies initiated (phase I CTM DS & DP) and interim report on stability studies on TOX lots available |  |  | 2- Alert to CTM1 | B | Interim report for ongoing stability studies – phase I and TOX lots |  |  | 3 - For inital auth | B | Stability studies on investigational stockpile according to ICH guidelines initiated |  |  | 4- Post D100 | B | Real-time stability studies initiated for phase IIb/III CTM DS & DP |  |  | 3 - For inital auth | B | Annual Product Quality Review program in place |  |  | 4- Post D100
| C | Adjuvant selected and used for TOX study (if applicable) |  |  | 1 - Preparation | C | Overall stability plan over product lifecycle to support intended shelf life established |  |  | 1 - Preparation | C | Define DS retest period and target DP shelf life |  |  | 3 - For inital auth | C | In-use stability under field conditions tested |  |  | 4- Post D100 | C | Product labelling strategy, and artwork finalized |  |  | 3 - For inital auth | C | Retest/shelf-life data update |  |  | 4- Post D100
| D | Real-time stability studies initiated on TOX lot |  |  | 2- Alert to CTM1 | D | MCB/MVS stability protocol in place |  |  | 1 - Preparation | [10 empty] | D | Sampling process, method, container, storage management, and record maintenance defined |  |  | 3 - For inital auth | D | Product integrated in the annual product review process and QMS system |  |  | 4- Post D100
[21 empty] | E | Retest/shelf-life data update |  |  | 4- Post D100 | E | Visual inspection defects gallery created |  |  | 4- Post D100
[21 empty] | F | Accelerated stability studies conducted |  |  | 3 - For inital auth | F | Stability studies completed: Stress, accelerated |  |  | 4- Post D100
[21 empty] | G | Accelerated and stress stability data for VVM available |  |  | 3 - For inital auth | G | In-use stability studies completed (if applicable) |  |  | 4- Post D100
[21 empty] | H | VVM qualification |  |  | 1 - Preparation
[21 empty] | I | In-use stability under field conditions tested |  |  | 4- Post D100
[21 empty] | J | Shelf life defined for key process intermediates, buffers, media |  |  | 3 - For inital auth
[21 empty] | K | MCB/MVS stability interim report available |  |  | 3 - For inital auth
Additional Considerations (N) | A | In-use stability identified |  |  | 1 - Preparation | A | Plan for development of final formulation, liquid/lyo/other |  |  | 1 - Preparation | A | Accelerated and stress stability data for VVM |  |  | 3 - For inital auth | A | Agitation, FT, in-use, photostability studies initiated |  |  | 3 - For inital auth | A | Cumulative stability testing protocol approved, and study initiated |  |  | 4- Post D100
| B | Short-term thermal stability |  |  | 1 - Preparation | B | Accelerated stability studies initiated |  |  | 2- Alert to CTM1 | B | Lyophilized formulation and process developed as backup (if required) |  |  | 1 - Preparation | B | VVM qualification |  |  | 3 - For inital auth | B | Evaluate feasibility of CTC (controlled temperature chain) claim (if applicable) |  |  | 4- Post D100
[11 empty] | C | In-use stability under field conditions tested |  |  | 4- Post D100 | C | Final formulation (according to TPP) stockpile DP |  |  | 3 - For inital auth | C | Visual inspection defects gallery created |  |  | 4- Post D100
[11 empty] | D | Kinetic modeling studies to estimate product stability at different temperatures |  |  | 1 - Preparation | [5 empty] | D | Shipping and cold chain validation studies completed |  |  | 4- Post D100
[11 empty] | E | Accelerated stability studies conducted |  |  | 3 - For inital auth | [5 empty] | E | Temperature excursion stability study initiated |  |  | 4- Post D100
[21 empty] | F | Photostability study or risk assessment completed |  |  | 4- Post D100
[21 empty] | G | Stability studies completed: Stress, accelerated |  |  | 4- Post D100
[21 empty] | H | DS/DP stability for registraton completed |  |  | 4- Post D100
[21 empty] | I | For combination products: Human Factor studies or relevant risk asssessment conducted and eventual Medical Device certification (ie. CE mark for EU) NOTE: this can be also available prior to BLA/MAA |  |  | 1 - Preparation
[21 empty] | J | In-use stability studies completed |  |  | 4- Post D100
[21 empty] | K | Product integrated in the annual product review process and QMS system |  |  | 4- Post D100
L
Phase I
Phase II
Investigational stockpile
Pre-clinical
Phase IIb/III pivotal study
Phase IIb/III pivotal study
Phase IV /post licensure

## DS and DP Analytical (hidden)
Drug Substance & Drug Product Analytics (QC)
| # | CMC deliverables during | Status | Comments | Rapid Response | # | CMC deliverables for | Status | Comments | Rapid Response | # | CMC deliverables for | Status | Comments | Rapid Response | # | CMC deliverables for | Status | Comments | Rapid Response | # | CMC deliverables for and during | Status | Comments | Rapid Response | # | CMC deliverables for and during | Status | Comments | Rapid Response
| 3.1 | Pre-clinical |  |  |  | 3.2 | Phase I |  |  |  | 3.3 | Phase II |  |  |  | 3.4 | Investigational stockpile |  |  |  | 3.5 | Phase IIb/III pivotal study |  |  |  | 3.6
High level definition |  | Analytical methods developed |  |  |  |  | Analytical methods scientifically sound |  |  |  |  | Analytical methods qualified |  |  |  |  | Potency assay validated |  |  |  |  | Analytical methods validated |  |  |  |  | Release to market
Expected requirements (M) | A | Methods developed (identity, potency, quantity, purity) |  | covered bucket 1+2 | 2- Alert to CTM1 | A | Phase appropriate specifications available |  | covered in bucket 1 | 2- Alert to CTM1 | A | Phase I material shown to be representative of Phase II material |  | covered | 3 - For inital auth | A | Phase appropriate validation of analytical methods |  | n/a | 3 - For inital auth | A | Release test methods validated |  | covered | 3 - For inital auth | A | Submissions plan for satisfying eventual commitments/agreements taken during the revision phase prior license approval |  | bucket 4 | 4- Post D100
| B | CoA for TOX material available |  | most likely the same as CTM1 | 2- Alert to CTM1 | B | TOX material shown to be representative of Phase I material |  | most likely the same material | 2- Alert to CTM1 | B | Phase appropriate validation of release assays and stability indicating assays (qualified) |  | covered | 3 - For inital auth | B | Potency assay validated at selected dose |  | n/a | 3 - For inital auth | B | Product specification in place - DS, formulated bulk, filled vial, FP, and FP at end of shelf life |  | covered | 2- Alert to CTM1 | B | Submission of all the Post approval changes (i.e. Bundle submission) |  |  | 4- Post D100
[6 empty] | C | Phase appropriate validation of release methods (qualified) |  | covered | 3 - For inital auth | C | All key analytical methods for characterization identified |  | covered bucket 1+2 | 2- Alert to CTM1 | C | Phase II material shown to be representative of investigational stockpile |  | n/a | 3 - For inital auth | C | Samples & reagents holding time defined |  |  | 3 - For inital auth | C | Methods of analysis validation, maintenance/repetition/confirmation according GMP and internal QMS |  |  | 4- Post D100
[6 empty] | D | Critical methods developed (for stability, characterization, and dose determination) |  | covered in bucket 1 | 2- Alert to CTM1 | D | Analytical methods risk assessment |  | Added to bucket 2 | 2- Alert to CTM1 | [5 empty] | D | RM testing methods validated and implemented, including stability/retest |  | covered in bucket 1 | 3 - For inital auth | D | Complete amino acid sequence determined and confirmed, along with the identification of any post-translational modifications (PTMs) (if applicable) |  | too detailed | 4- Post D100
[6 empty] | E | IPCs identified |  | platform? | 2- Alert to CTM1 | E | Reference standard for phase II in place |  |  | 3 - For inital auth | [5 empty] | E | Analytical content of Module 3 prepared & peer reviewed |  | covered | 3 - For inital auth | E
[6 empty] | F | Analytical validation master plan in place |  | covered in bucket 1 | 1 - Preparation | [10 empty] | F | Process and product impurities characterized and control strategy in place. If required, clearance during process and lack of toxicity demonstrated. |  |  | 3 - For inital auth | F
[6 empty] | G | Strategy for release / export to CROs in place |  | covered in bucket 1 | 1 - Preparation | [10 empty] | G | Reference standard strategy in place |  | covered | 3 - For inital auth | G
[6 empty] | H | Preliminary reference standard in place for CTM release for phase I |  | Added to bucket 2 | 2- Alert to CTM1 | [10 empty] | H | Strategy for national release (e.g. NCLs, OMCLs) defined |  | covered | 3 - For inital auth | H
[6 empty] | I | Release, characterization, and stability methods for MCB/MVS in place |  | covered in bucket 1 | 1 - Preparation | [10 empty] | I | Regulatory and analytical strategy aligned |  |  | 3 - For inital auth | I
[6 empty] | J | Amino acid sequence determination established (if applicable) |  | covered in bucket 1 | 1 - Preparation | [10 empty] | J | Additional samples testing plan in place (as part of PV) |  | bucket 4 | 4- Post D100 | J
[21 empty] | K | CCIT method qualified |  | covered in bucket 1 | 3 - For inital auth | K
[21 empty] | L | Complete amino acid sequence determined and confirmed (if applicable) |  | too detailed | 2- Alert to CTM1 | L
[21 empty] | M | Comparability shown between small scale and large scale, including previous CTM |  | bucket 4 | 4- Post D100 | M
[21 empty] | N | Reference standard for phase III in place |  |  | 3 - For inital auth | N
[21 empty] | O | Analytical validation master plan report available |  | bucket 4 | 4- Post D100
Additional Considerations (N) | A | Characterization methods developed |  | covered | 2- Alert to CTM1 | A | Release methods validated |  | covered | 3 - For inital auth | A | Potency method validated |  | covered | 2- Alert to CTM1 | [5 empty] | A | Pack Material testing process available |  |  | 3 - For inital auth | A | Master qualification protocols for Reference Standards (ideal to be present within the first MAA application) |  |  | 4- Post D100
| B | Initial CQAs and IPCs identified |  | IPC? | 1 - Preparation | B | Critical methods qualified (for stability, characterization, and dose determination) |  | covered | 3 - For inital auth | B | Release methods validated |  | covered | 3 - For inital auth | [5 empty] | B | Characterization protocol in place for in vitro test methods to replace in vivo |  | platform | 1 - Preparation | B | Master qualification protocols for Positive and Negative controls (ideal to be present within the first MAA application) |  |  | 4- Post D100
[6 empty] | C | Analytical maturity questionnaire completed |  | CEPI specific | 4- Post D100 | C | Stability indicating methods validated |  | covered | 3 - For inital auth | [5 empty] | C | Analytical methods / reference standards / critical reagents transferred to NCLs of target countries |  |  | 4- Post D100 | C
[11 empty] | D | Analytical methods tech transfer |  | covered | 2- Alert to CTM1 | [5 empty] | D | Antimicrobial effectiveness test - for multidose presentation |  | platform | 1 - Preparation | D
[11 empty] | E | Control cell testing - for testing of adventitious agents |  | covered | 1 - Preparation | [5 empty] | E | Equipment/instrument qualification master protocol in place |  | platform | 1 - Preparation | E
[11 empty] | F | Characaterization testing for impurities and if required to demonstrate clearing during process and lack of toxicity |  | covered | 1 - Preparation | [10 empty] | F
Pre-clinical
Phase I
Phase II
Investigational stockpile
Pre-clinical
Phase IIb/III pivotal study
Phase IV /post licensure
Note on K11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: for export to CRO you need to know where the outbreak is Reply: Not for the strategy. Unless it's Dis X, you can narrow down to endemic areas in the first instance Reply: Export/import preparations are covered under SC
Note on K14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: How can you do this before you have the sequence? The actual method should be covered by platform analytics. Reply: I interpreted the "sequence determination established" as "determination method established", else it's just "sequence determined" and the deliverable wording could be sharpened accordingly? Reply: Should be covered by platform then

## Supply Chain & COGS (hidden)
Supply Chain & COGS (SC)
| # | CMC deliverables during | Status | Comments | Rapid Response | # | CMC deliverables for | Status | Comments | Rapid Response | # | CMC deliverables for | Status | Comments | Rapid Response | # | CMC deliverables for | Status | Comments | Rapid Response | # | CMC deliverables for and during | Status | Comments | Rapid Response | # | CMC deliverables for and during | Status | Comments | Rapid Response
| 4.1 | Pre-clinical |  |  |  | 4.2 | Phase I |  |  |  | 4.3 | Phase II |  |  |  | 4.4 | Investigational stockpile |  |  |  | 4.5 |  |  |  |  | 4.6
High level definition |  | Freedom to operate assessed |  |  |  |  | All raw materials are suitable and sourceable |  |  |  |  | Supply Chain Strategy and COGS check |  |  |  |  | Product chain of custody and storage defined |  |  |  |  | Supply strategy established |  |  |  |  | Market supply
Expected requirements (M) | A | IP - freedom to operate assessed |  |  | 2- Alert to CTM1 | A | All raw materials of animal origin free source, or used along with required certificate (e.g. TSE / BSE free) |  |  | 2- Alert to CTM1 | A | COGS estimation/target COGS available |  |  | 1 - Preparation | A | Supply chain defined, including cold chain and GSP - 3PL identified |  |  | 1 - Preparation | A | Freedom to operate secured |  |  | 2- Alert to CTM1 | A | Stockpile concept developed including stock rotation policy and inventory replenishment |  |  | 4- Post D100
| B | Market risk analysis for supply constrained materials available |  |  | 1 - Preparation | B | Definition of supply chain strategy for clinical and commercial initiated: CMO selection, critical material, analytical strategy for outsourced testing |  |  | 1 - Preparation | B | Investigational stockpile storage defined |  |  | 3 - For inital auth | B | Investigational stockpile back up / intermediate storage locations identified |  |  | 4- Post D100 | B | Shipment validation completed - samples, WCB vials, intermediates, process product & FP (intra – inter site, flight path) |  |  | 2- Alert to CTM1 | B | Distribution capacity identified |  |  | 4- Post D100
| C | GMP grade raw materials available and sourced |  |  | 1 - Preparation | [5 empty] | C | Clinical supplies manufacturing plan defined |  |  | 2- Alert to CTM1 |  | Distribution strategy for investigational stockpile in place |  |  | 2- Alert to CTM1 | C | IT infrastructure to manage forecast, orders, Inventories, shipments, invoicing, is available. Product, raw material codes defined. |  |  | 3 - For inital auth | C | Sufficient workforce capability and capacity available |  |  | 4- Post D100
| D | [9 empty] | D | Supply chain strategy defined and SC Maturity Assessment completed |  | Partly CEPI internal | 4- Post D100 | [5 empty] | D | Contracts for cold chain suppliers - developing and qualifying cold trucks, samples and product shipment - agreement with cold chain samples in place |  |  | 1 - Preparation | D | Supply chain maturity level assessment updated and improvement plan in place (if applicable) |  |  | 4- Post D100
| E | [9 empty] | E | Storage requirements and infrastructure for raw material, intermediate and finish products evaluated |  |  | 1 - Preparation | [5 empty] | E | Commercial import license for RM, intermediates and FP in place |  |  | 2- Alert to CTM1 | E | Raw material replenishment strategy in place |  |  | 4- Post D100
| F | [19 empty] | F | BOM defined. Process in place for issuance and return of the materials, disposal of unused, waste non-biological hazard materials |  |  | 2- Alert to CTM1 | F | COGS defined for the commercial supply. Scenario building – additional capacities, in – house vs outsourcing |  |  | 4- Post D100
| G | [19 empty] | G | CMAs identified, life cycle defined |  |  | 2- Alert to CTM1 | G | Stockpile distribution strategy in place (if applicable) |  |  | 4- Post D100
| H | [19 empty] | H | Strategic raw material stock in place if it is needed as mitigation plan |  |  | 4- Post D100 | H
| I | [19 empty] | I | Raw material qualification complete |  |  | 2- Alert to CTM1 | I
| J | [19 empty] | J | Supply agreements in place for all raw materials and consumables |  |  | 2- Alert to CTM1 | J
| K | [24 empty] | K
| L | [24 empty] | L
Additional Considerations (N) | A |  |  |  |  | A | Sensitivity analysis performed |  |  | 1 - Preparation | A | Investigational stockpile distribution plan defined |  |  | 4- Post D100 | A |  |  |  |  | A | Critical materials management plan in place - materials with single vendor, critical materials with risk in supply, alterative vendor development, developing compliant vendors - 3R principles, non-biological origin materials etc. |  |  | 1 - Preparation | A
| B |  |  |  |  | B | Initial COGS estimated |  |  | 1 - Preparation | B | Modelling & Design of multiproduct facilities |  |  | 1 - Preparation | B |  |  |  |  | B | Strategy designed for reverse supply chain or single use containers / materials |  |  | 1 - Preparation | B
| C |  |  |  |  | C | Development cost estimated |  |  | 1 - Preparation | C | CMAs identified, life cycle defined |  |  | 2- Alert to CTM1 | C |  |  |  |  | C | Product capacity assumptions defined - batch yield / batch; Average loss / process step; No. of batches / year; Millions of doses / year |  |  | 2- Alert to CTM1 | C
| D |  |  |  |  | D | SC Maturity Assessment completed |  | CEPI specific | 4- Post D100 | D | Supply chain review of CMC modules for CTA and Registration file |  |  | 3 - For inital auth | D |  |  |  |  | D | COGS defined for commercial supply. Scenario building – additional capacities, in-house vs. outsourcing |  |  | 4- Post D100 | D
| E |  |  |  |  | E |  |  |  |  | E | Development cost updated |  |  | 4- Post D100 | E |  |  |  |  | E | COGS vs additional capacity / CDMO approach assessed |  |  | 1 - Preparation | E
| F |  |  |  |  | F |  |  |  |  | F | Process available in simulation model |  |  | 4- Post D100 | F |  |  |  |  | F |  |  |  |  | F
[11 empty] | G | Capacity analysis (process bottlenecks identified) |  |  | 4- Post D100
Pre-clinical
Phase I
Phase II
Investigational stockpile
Pre-clinical
Phase IIb/III pivotal study
Phase IV /post licensure

## Facility and Compliance (hidden)
Facility and Compliance (GMP)
| # | CMC deliverables during | Status | Comments | Rapid Response | # | CMC deliverables for | Status | Comments | Rapid Response | # | CMC deliverables for | Status | Comments | Rapid Response | # | CMC deliverables for | Status | Comments | Rapid Response | # | CMC deliverables for and during | Status | Comments | Rapid Response | # | CMC deliverables for and during | Status | Comments | Rapid Response
| 5.1 | Pre-clinical |  |  |  | 5.2 | Phase I |  |  |  | 5.3 | Phase II |  |  |  | 5.4 | Investigational stockpile |  |  |  | 5.5 |  |  |  |  | 5.6
High level definition |  | GMP readiness preparation including the development of PQS |  |  |  |  | GMP Compliant manufacturing and testing facilities including functional PQS |  |  |  |  | GMP Compliant manufacturing and testing facilities including functional PQS |  |  |  |  | GMP Compliant storage facility including a robust PQS |  |  |  |  | GMP Compliant manufacturing and testing facilities including a robust PQS |  |  |  |  | GMP Compliant manufacturing and testing facilities including mature PQS
Expected requirements (M) | A | TOX material manufactured under appropriate conditions |  |  | 2- Alert to CTM1 | A | GMP certification and MIA for IMPs available (Manufacturing License(s)) |  |  | 1 - Preparation | A | GMP certification and MIA for IMPs available (Manufacturing License(s)) |  |  | 1 - Preparation | A | QP declaration Annex 5.22 as per EU MAA (if applicable) |  |  | 1 - Preparation | A | GMP certification and MIA for IMPs available (Manufacturing License(s)) |  |  | 1 - Preparation | A | QP declaration Annex 5.22 as per EU MAA (if applicable) |  |  | 4- Post D100
| B | GMP Clinical Material Manufacturing site(s) identified |  |  | 2- Alert to CTM1 | B | QP declaration Annex 5.22 as per EU MAA (if applicable) |  |  | 2- Alert to CTM1 | B | QP declaration Annex 5.22 as per EU MAA (if applicable) |  |  | 2- Alert to CTM1 | B | Marketing Authorisations (EUA, investigational) in place |  |  | 2- Alert to CTM1 | B | QP declaration Annex 5.22 as per EU MAA (if applicable) |  |  | 3 - For inital auth | B | Completed (independent) GMP Inspection Assessment |  |  | 4- Post D100
| C | Phase appropriate Site Master File in place |  |  | 1 - Preparation | C | GMP manufactured and released clinical material |  |  | 2- Alert to CTM1 | C | GMP manufactured and released clinical material |  |  | 2- Alert to CTM1 | C | GMP manufactured and released clinical material (if applicable) |  |  | 2- Alert to CTM1 | C | GMP manufactured and released clinical material |  |  | 2- Alert to CTM1 | C | Marketing approval authorized |  |  | 4- Post D100
| D |  |  |  |  | D | Phase appropriate GMP compliant PQS established |  |  | 1 - Preparation | D | Phase appropriate GMP compliant PQS established |  |  | 1 - Preparation | D | Phase appropriate GMP compliant PQS established |  |  | 1 - Preparation | D | Phase appropriate GMP compliant PQS established |  |  | 1 - Preparation | D | MIA/GMP maintained with regular HA inspections for Commercial Facility |  |  | 4- Post D100
| E |  |  |  |  | E | Phase appropriate Quality Risk Management and risk register processes in place |  |  | 1 - Preparation | E | Phase appropriate Quality Risk Management and risk register processes in place |  |  | 1 - Preparation | E | Phase appropriate Quality Risk Management and risk register processes in place |  |  | 1 - Preparation | E | Phase appropriate Quality Risk Management and risk register processes in place |  |  | 1 - Preparation | E | Phase appropriate GMP compliant PQS established |  |  | 4- Post D100
| F |  |  |  |  | F | Phase appropriate QMS Management review process in place |  |  | 1 - Preparation | F | Phase appropriate QMS Management review process in place |  |  | 1 - Preparation | F | Phase appropriate QMS Management review process in place |  |  | 1 - Preparation | F | Phase appropriate QMS Management review process in place |  |  | 1 - Preparation | F | Phase appropriate Quality Risk Management and risk register processes in place |  |  | 4- Post D100
| G |  |  |  |  | G | Phase appropriate Continuous Improvement built into the PQS |  |  | 1 - Preparation | G | Phase appropriate Continuous Improvement built into the PQS |  |  | 1 - Preparation | G | Phase appropriate Continuous Improvement built into the PQS |  |  | 1 - Preparation | G | Phase appropriate Continuous Improvement built into the PQS |  |  | 1 - Preparation | G | Phase appropriate QMS Management review process in place |  |  | 4- Post D100
| H |  |  |  |  | H | Phase appropriate GDP practices in place |  |  | 1 - Preparation | H | Phase appropriate GDP practices in place |  |  | 1 - Preparation | H | Phase appropriate GDP practices in place |  |  | 1 - Preparation | H | Phase appropriate GDP practices in place |  |  | 1 - Preparation | H | Phase appropriate Continuous Improvement built into the PQS |  |  | 4- Post D100
| I |  |  |  |  | I | Quality oversight of outsourced activities (Audit process) in place |  |  | 1 - Preparation | I | Quality oversight of outsourced activities (Audit process) in place |  |  | 1 - Preparation | I | Quality oversight of outsourced activities (Audit process) in place |  |  | 1 - Preparation | I | Quality oversight of outsourced activities (Audit process) in place |  |  | 1 - Preparation | I | Phase appropriate GDP practices in place |  |  | 4- Post D100
| J |  |  |  |  | J | Quality and Technical Agreements in place |  |  | 1 - Preparation | J | Quality and Technical Agreements in place |  |  | 1 - Preparation | J | Quality and Technical Agreements in place |  |  | 1 - Preparation | J | Quality and Technical Agreements in place |  |  | 3 - For inital auth | J | Quality oversight of outsourced activities (Audit process) in place |  |  | 4- Post D100
| K |  |  |  |  | K | Phase appropriate Cross Contamination Prevention strategy in place |  |  | 1 - Preparation | K | GMP Commercial Material Manufacturing site(s) identified (if applicable) |  |  | 3 - For inital auth | K | Phase appropriate Cross Contamination Prevention strategy in place |  |  | 3 - For inital auth | K | GMP Commercial Material Manufacturing sites(s) identified |  |  | 3 - For inital auth | K | Quality and Technical Agreements in place |  |  | 4- Post D100
| L |  |  |  |  | L | Phase appropriate Aseptic Qualification of personnel |  |  | 1 - Preparation | L | Phase appropriate Cross Contamination Prevention strategy in place |  |  | 1 - Preparation | L | Phase appropriate Aseptic Qualification of personnel |  |  | 1 - Preparation | L | Phase appropriate Cross Contamination Prevention strategy in place |  |  | 1 - Preparation | L | GMP Commercial Material Manufacturing sites(s) identified |  |  | 4- Post D100
| M |  |  |  |  | M | Phase appropriate Equipment Maintenance and Calibration strategy in place |  |  | 1 - Preparation | M | Phase appropriate Aseptic Qualification of personnel |  |  | 1 - Preparation | M | Phase appropriate Equipment Maintenance and Calibration strategy in place |  |  | 1 - Preparation | M | Phase appropriate Aseptic Qualification of personnel |  |  | 1 - Preparation | M | Phase appropriate Cross Contamination Prevention strategy in place |  |  | 4- Post D100
| N |  |  |  |  | N | Phase Appropriate Qualification of Facilities, Utilities and Equipment in place |  |  | 1 - Preparation | N | Phase appropriate Equipment Maintenance and Calibration strategy in place |  |  | 1 - Preparation | N | Phase Appropriate Qualification of Facilities, Utilities and Equipment in place |  |  | 1 - Preparation | N | Phase appropriate Equipment Maintenance and Calibration strategy in place |  |  | 1 - Preparation | N | Phase appropriate Aseptic Qualification of personnel |  |  | 4- Post D100
| O |  |  |  |  | O | Phase appropriate Technology Transfer process for Equipment, Utilities and Facility in place |  |  | 1 - Preparation | O | Phase Appropriate Qualification of Facilities, Utilities and Equipment in place |  |  | 1 - Preparation | O | Phase appropriate Technology Transfer process for Equipment, Utilities and Facility in place |  |  | 1 - Preparation | O | Phase Appropriate Qualification of Facilities, Utilities and Equipment in place |  |  | 1 - Preparation | O | Phase appropriate Equipment Maintenance and Calibration strategy in place |  |  | 4- Post D100
| P |  |  |  |  | P | Phase appropriate Enviromental monitioring strategy in place |  |  | 1 - Preparation | P | Phase appropriate Technology Transfer process for Equipment, Utilities and Facility in place |  |  | 1 - Preparation | P | Phase appropriate Enviromental monitioring strategy in place |  |  | 1 - Preparation | P | Phase appropriate Technology Transfer process for Equipment, Utilities and Facility in place |  |  | 1 - Preparation | P | Phase Appropriate Qualifiation of Facilities, Utilities and Equipment in place |  |  | 4- Post D100
| Q |  |  |  |  | Q | Phase appropriate Utilities monitoring in place |  |  | 1 - Preparation | Q | Phase appropriate Enviromental monitioring strategy in place |  |  | 1 - Preparation | Q | Phase appropriate Utilities monitoring in place |  |  | 1 - Preparation | Q | Phase appropriate Enviromental monitioring strategy in place |  |  | 1 - Preparation | Q | Phase appropriate Technology Transfer process for Equipment, Utilities and Facility in place |  |  | 4- Post D100
| R |  |  |  |  | R | Phase appropriate Raw Material strategy in place |  |  | 1 - Preparation | R | Phase appropriate Utilities monitoring in place |  |  | 1 - Preparation | R | Phase appropriate Raw Material strategy in place |  |  | 1 - Preparation | R | Phase appropriate Utilities monitoring in place |  |  | 1 - Preparation | R | Phase appropriate Enviromental monitioring strategy in place |  |  | 4- Post D100
| S |  |  |  |  | S | Phase appropriate Site Master File in place |  |  | 1 - Preparation | S | Phase appropriate Raw Material strategy in place |  |  | 1 - Preparation | S | Phase appropriate strategy for Prevention of Falsified Medicines in place |  |  | 1 - Preparation | S | Phase appropriate Raw Material strategy in place |  |  | 1 - Preparation | S | Phase appropriate Utilities monitoring in place |  |  | 4- Post D100
| T |  |  |  |  | T | Additional licenses (as applicable to the processes and technologies being used, eg CE mark, ISO 13485) in place |  |  | 1 - Preparation | T | Phase appropriate Site Master File in place |  |  | 1 - Preparation | T | Phase appropriate Site Master File in place |  |  | 1 - Preparation | T | Phase appropriate Site Master File in place |  |  | 3 - For inital auth | T | Phase appropriate Raw Material strategy in place |  |  | 4- Post D100
[6 empty] | U |  |  |  |  | U | Additional licenses (as applicable to the processes and technologies being used, eg CE mark, ISO 13485) in place |  |  | 1 - Preparation | U | Additional licenses (as applicable to the processes and technologies being used, eg CE mark, ISO 13485) in place |  |  | 1 - Preparation | U | Additional licenses (as applicable to the processes and technologies being used, eg CE mark, ISO 13485) in place |  |  | 1 - Preparation | U | Phase appropriate strategy for Prevention of Falsified Medicines in place |  |  | 4- Post D100
[6 empty] | V |  |  |  |  | V |  |  |  |  | V |  |  |  |  | V | Marketing Authorisation Holder identified (if applicable) |  |  | 3 - For inital auth | V | Phase appropriate Site Master File in place |  |  | 4- Post D100
[26 empty] | W | Additional licenses (as applicable to the processes and technologies being used, eg CE mark, ISO 13485) in place |  |  | 4- Post D100
Additional Considerations (N) | A | CMC for matchmaking |  | CEPI specific | 4- Post D100 | A |  |  |  |  | A |  |  |  |  | A | CMC for matchmaking |  | CEPI specific | 4- Post D100 | A |  |  |  |  | A
| B |  |  |  |  | B |  |  |  |  | B |  |  |  |  | B |  |  |  |  | B |  |  |  |  | B
| C |  |  |  |  | C |  |  |  |  | C |  |  |  |  | C |  |  |  |  | C |  |  |  |  | C
Phase I
Phase II
Investigational stockpile
Pre-clinical
Phase IIb/III pivotal study
Phase IV /post licensure

## Abbreviations
Abbreviation | Spelled out
3-PL | Third-party logistics |  | Buckets
3R | Replacement, Reduction and Refinement |  | 1 - Preparation
BDS | Bulk Drug Substrance |  | 2- Alert to CTM1
BLA | Biologics License Application |  | 3 - For inital auth
BOM | Bill of Materials |  | 4- Post D100
BSE | Bovine spongiform encephalopathy
CCIT | Container Closure Integrity Testing
CDMO | Contract Developer & Manufacturing Organization
CE | Conformité Européenne
CIP | Cleaning in Place
CMA | Critical Material Attribute
CMC | Chemistry Manufacture Controls
CMO | Contract Manufacturing Organization
CoA | Certificate of Analysis
COGS | Cost of Goods Sold
CRO | Contract Research Organization
CPP | Critical Process Parameter
CQA | Critical Quality Attributes
CTA | Clinical Trial Application
CTC | Controlled temperature chain
CTM | Clinical Trial Material
DD | Due Diligence | Not needed for external
DP | Drug Product
DS | Drug Substance
E&L | Extractables & Leachables
EU | European Union
EUA | Emergency Use Authorization
FP | Finished Product
FT | Freeze/Thaw
GDP | Good Distribution Practices
GMP | Good Manufacturing Practices
GSP | Global Shipping Program
HA | Health Authority
ICH | International Conference on Harmonization
IMP | Investigation Medicinal Product
IMPD | Investigation Medicinal Product Dossier (clinical trial material filing)
IND | Investigational Drug
IP | Intellectual Property
IPC | In Process Control
ISO | International Organization for Standardization
IT | Information Technology
KPP | Key Process Parameter
LCM | Life Cycle Management
lyo | Lyophilized
MAA | Marketing Authorisation Applications
MBR | Manufacturing Batch Record
MCB | Master Cell Bank
MIA | Manufacturing and Import Authorisation
MSAT | Manufacturing Science and Technology
MVS | Master Virus Seed
NCL | National Control Laboratory
OMCL | Official Medicines Control Laboratories
PFD | Process Flow Diagram
PPQ | Process Performance Qualification
PQ | Process OR Product OR Performance Qualification
PQS | Pharmaceutical Quality Systems
PV | Process Validation (see also PQ/PPQ)
PTMs | Post-translational modifications
QA | Quality Assurance
QC | Quality Control
QMS | Quality Management System
QP | Qualified Person
QTTP | Quality Target Product Profile
RA | Regulatory Affairs
RCB | Research Cell Bank
RM | Raw Material
SC | Supply Chain | Not needed for external
SG | Stage Gate | Not needed for external
SIP | Steam or Sanitize in Place
TFF | Tangential Flow Filtration
TOC | Total Organic Carbon
TOX | Toxicity / preclinical study
TPP | Target Product Profile
TSE | Transmissible Spongiform Encephalopathies
TT | Tech Transfer
VVM | Vaccine Vial Monitor
WCB | Working Cell Bank
WVS | Working Virus Seed